Requirements Traceability Matrix (RTM) & Data Analysis Report

HealthFirst Care Initiative: Patient Experience & Operational Efficiency Overhaul

| Document Title: | Capstone_Project_M01L02_RTM.doc |
| --- | --- |
| Project Name: | HealthFirst Care Initiative |
| Author / Analyst: | Pritam Kar |
| Date : | August 18, 2026 |

# Task 1: Project Context & Stakeholder Analysis

The HealthFirst Care Initiative targets systemic operational bottlenecks across hospital workflows. Primary objectives focus on resolving extended patient wait times, frequent appointment double-bookings, severe resource deficits, and communication gaps.

Stakeholder Roles & Core Challenges:

Patients (Sarah Ayvazyan, Lak Ayer): Experiencing excessive wait times and lacking real-time updates regarding appointment delays.

Doctors & Nurses (Dr. Aftab Khan, Dr. Robert Lee, Santa Murmu): Facing high daily workload strain and scheduling friction caused by booking conflicts.

Administrative Staff (Maria Carter, Jessica Gomes): Struggling with manual entry errors and uncoordinated scheduling workflows.

IT & Operations Management (Rajesh Singh, Laura Simkow, Ivan Walker): Managing legacy storage systems, HIPAA compliance requirements, and system throughput during peak hours.

# Task 2 & Task 3: Requirements Traceability Matrix (RTM)

| Requirement ID | Requirement Description | Priority Level (MoSCoW) | Stakeholder(s) | Project Objective | Related Data File | Status |
| --- | --- | --- | --- | --- | --- | --- |
| FR-01 | Automated Conflict Prevention Engine: System must validate doctor, room, and equipment availability before confirming bookings to eliminate double-booking incidents. | Must Have | Maria Carter (Scheduler), Dr. Aftab Khan, Dr. Robert Lee | AC-02: Eliminate double bookings (achieve 0 double-booking incidents). | appointment_data.csv | Approved |
| FR-02 | Live Resource Tracking & Management: Real-time availability dashboard (Available, In Use, Under Maintenance) for rooms, diagnostic gear, and staff. | Must Have | Dr. Robert Lee, Santa Murmu, Jessica Gomes | AC-04: Achieve >= 70% resource availability during peak hours. | resource_data.csv | Approved |
| FR-03 | Automated Patient Notification Service: Real-time SMS/Email alerts for booking confirmations, queue delays, and 24-hour appointment reminders. | Must Have | Sarah Ayvazyan, Lak Ayer, Laura Simkow | AC-01 & AC-03: Reduce wait times <= 33.1 min and boost satisfaction >= 8.0/10. | feedback_data.csv | Approved |
| FR-04 | Integrated Patient Record Management: Centralized system linking billing, scheduling, and patient history to eliminate data silos. | Should Have | Ivan Walker (Billing), Rajesh Singh (IT Manager) | Eliminate departmental data silos and streamline billing/treatment records. | feedback_data.csv | Draft |
| NFR-01 | System Scalability & Performance: Cloud-enabled architecture ensuring 99.9% uptime during peak booking windows (17:00–18:30). | Must Have | Rajesh Singh (IT Manager) | Infrastructure stability and seamless data flow across departments. | appointment_data.csv | Approved |
| NFR-02 | Data Security & Compliance: Role-based security access, end-to-end encryption, and full HIPAA compliance for patient data protection. | Must Have | Laura Simkow (Developer), IT & Operations | Address security vulnerabilities in legacy architecture. | N/A | Approved |
| NFR-03 | User-Friendly Interface (UI/UX): Simplified, intuitive web/mobile self-service portal for multi-generational patient access. | Should Have | Lak Ayer, Sarah Ayvazyan | Reduce booking friction and direct support desk call volume. | feedback_data.csv | Draft |

# Task 4: Analysis of Data Files

appointment_data.csv (216 Records): Analysis confirms severe scheduling flaws, revealing 32 double-booking instances (same doctor, date, and time slot). Only 26.8% of appointments reach completion, while 73.2% fail due to No-Shows (24.1%), Rescheduling (23.1%), and Cancellations (21.8%). Peak booking volume occurs between 17:00–18:30. This directly justifies FR-01 (Automated Conflict Prevention) and NFR-01 (System Scalability).

feedback_data.csv (217 Records): Patient feedback highlights an average wait time of 41.4 minutes across departments (peaking in General Medicine at 43.9 min and Orthopedics at 42.0 min). This excessive wait depresses average patient satisfaction scores to 6.3 / 10. Qualitative complaints cite a lack of delay notifications and clear instructions, justifying FR-03 (Automated Patient Notification Service) and NFR-03 (User-Friendly Interface).

resource_data.csv (213 Records): Hospital resource logs indicate a severe availability deficit, with 42.7% of resources unavailable (30.5%) or under maintenance (12.2%). Significant workload imbalances exist, with Orthopedics doctors averaging 7.86 usage hours/day while Cardiology doctors have unmapped hours. This directly justifies FR-02 (Live Resource Tracking & Management).

# Task 5: RTM Validation Summary Checklist

| Validation Checkpoint | Status | Validation Summary Notes |
| --- | --- | --- |
| BRD Requirements Alignment | CONFIRMED | All functional requirements (FR-01 to FR-04) and core constraints outlined in the BRD are fully mapped. |
| Stakeholder Needs Coverage | CONFIRMED | Pain points from Patients, Doctors, Nurses, Admin, and IT teams are directly linked to system requirements. |
| Data File Justification | CONFIRMED | Every key functional requirement is explicitly justified by empirical evidence from the three CSV files. |
| MoSCoW Prioritization | CONFIRMED | Requirements are categorized into Must Have and Should Have to guide phase planning. |
| Objective Traceability | CONFIRMED | All requirements directly link to target acceptance criteria (AC-01 through AC-04). |