RISK MATRIX & MITIGATION PLAN

HealthFirst Care Initiative: Patient Experience & Operational Efficiency Overhaul

| Document Title: | Capstone_Project_M05L02_Risk_Matrix_Mitigation.docx |
| --- | --- |
| Project Name: | HealthFirst Care Initiative |
| Author / Analyst: | Pritam Kar |
| Date: | September 1, 2026 |
| Source Documents: | Capstone_Project_M05L01_Risk_Register_SWOT.docx; HealthFirst_Care_Risk_Register.xlsx |

# Executive Summary

This Risk Mitigation Plan builds on the Risk Register and SWOT Analysis developed in Module 5, Lesson 1 (Capstone_Project_M05L01_Risk_Register_SWOT.docx and its companion workbook, HealthFirst_Care_Risk_Register.xlsx). It updates the Risk Matrix with mitigation strategies for all fifteen identified risks and adds detailed contingency plans for the seven High-severity risks, ensuring the HealthFirst Care Initiative remains resilient if a prioritized risk materializes despite mitigation efforts.

Seven risks scored High severity (score 6-9): OP-01, OP-03, OP-04, OP-05, TE-02, TE-04, and ST-05. These concentrate around staffing and workload rebalancing, peak-hour system reliability, and patient engagement with automated notifications — the same themes identified across the BRD, process models, and stakeholder analysis. Each is addressed below with both a proactive mitigation strategy and a reactive contingency plan.

# Task 1: Updated Risk Matrix with Mitigation Strategies

The table below reproduces the full Risk Register with likelihood, impact, and severity scoring, and includes the Mitigation Strategy column proposed for each risk to proactively reduce its likelihood or impact.

| Risk ID | Risk Description | Category | Likelihood | Impact | Score | Severity | Mitigation Strategy |
| --- | --- | --- | --- | --- | --- | --- | --- |
| OP-01 | Administrative schedulers resist adopting the automated conflict-prevention engine, continuing manual workarounds that reintroduce double-booking risk. | Operational | Medium | High | 6 | High | Phased rollout with a parallel-run period; structured change-management plan with weekly hands-on training sessions for schedulers. |
| OP-02 | Mandatory staff training on kiosks and the new scheduling platform is incomplete before go-live, causing usage errors at launch. | Operational | Medium | Medium | 4 | Medium | Require training certification checkpoints prior to rollout; staff a dedicated super-user support desk for the first two weeks post-launch. |
| OP-03 | Billing-issue resolution at discharge has no defined turnaround time, so the Admin/Billing bottleneck persists after automation. | Operational | High | Medium | 6 | High | Define a service-level target (e.g., 2-hour resolution) for billing exceptions with automatic escalation to a billing supervisor when breached. |
| OP-04 | Peak-hour congestion (Monday/weekend, 4-6 PM window) continues even after booking automation, since the root cause is staffing capacity, not scheduling conflicts alone. | Operational | High | High | 9 | High | Rebalance staffing schedules toward Monday, weekend, and 4-6 PM shifts using the appointment volume trends already identified; add temporary float staff during peak windows. |
| OP-05 | Severe workload imbalance (Orthopedics doctors averaging 7.86 usage hrs/day) is not resolved by scheduling automation alone, risking clinician burnout. | Operational | Medium | High | 6 | High | Configure the live resource dashboard to trigger automatic workload-rebalancing alerts to leadership; establish a cross-department staff-pooling protocol for peak periods. |
| TE-01 | Cloud-enabled EHR integration with legacy patient-data architecture introduces a data breach or HIPAA compliance gap. | Technical | Low | High | 3 | Medium | Enforce role-based access control and end-to-end encryption (NFR-02); commission a third-party security audit and penetration test before go-live. |
| TE-02 | The scheduling/EHR platform experiences downtime or slow response during the 17:00-18:30 peak booking window, breaching the 99.9% uptime target. | Technical | Medium | High | 6 | High | Load-test the platform at 2x observed peak volume before launch; deploy redundant failover infrastructure with real-time uptime monitoring and alerting. |
| TE-03 | Interoperability issues between the new platform and the legacy database cause data integrity errors during integration. | Technical | Medium | Medium | 4 | Medium | Run a phased data migration with reconciliation checks against the legacy source; validate in a sandbox environment before production cutover. |
| TE-04 | The real-time conflict-detection engine fails to catch edge cases (concurrent bookings, sync lag), so double-bookings are reduced but not fully eliminated (AC-02 at risk). | Technical | Medium | High | 6 | High | Stress-test the conflict engine under concurrent-load scenarios; maintain a manual override queue with an audit log for administrative review. |
| TE-05 | Self-service kiosks or QR check-in hardware malfunction, forcing a fallback to manual paperwork and reintroducing the front-desk wait-time bottleneck. | Technical | Low | Medium | 2 | Low | Establish a preventive hardware maintenance schedule; keep a staffed manual backup lane available during outages. |
| ST-01 | Patients, particularly older or less tech-familiar users, show poor adoption of the web/mobile self-service portal, undermining the wait-time and satisfaction targets (AC-01, AC-03). | Stakeholder | Medium | Medium | 4 | Medium | Apply the simplified, multi-generational UI/UX design called for in NFR-03; provide on-site staff assistance for portal onboarding during the transition period. |
| ST-02 | Expectations diverge between IT & Operations (Keep Satisfied) and clinical Key Players on rollout timeline and feature priorities. | Stakeholder | Medium | Medium | 4 | Medium | Maintain the bi-weekly IT architecture syncs and weekly clinical status meetings defined in the Stakeholder Engagement Plan to keep priorities aligned. |
| ST-03 | Low engagement from Support & Maintenance staff (Monitor quadrant) leads to facility or equipment readiness gaps ahead of rollout milestones. | Stakeholder | Low | Medium | 2 | Low | Use intranet bulletins and scheduled facility-readiness check-ins tied to each project milestone date. |
| ST-04 | Doctors and nurses resist workload-rebalancing recommendations surfaced by the live resource dashboard (e.g., shifting load away from Orthopedics). | Stakeholder | Medium | Medium | 4 | Medium | Involve physicians and nurses directly in schedule-design feedback workshops; phase in rebalancing gradually and share transparent utilization data. |
| ST-05 | Patients continue to distrust or ignore automated SMS/Email notifications, so the 73.2% non-completion rate (no-shows, reschedules, cancellations) does not meaningfully improve. | Stakeholder | Medium | High | 6 | High | A/B test notification timing and channel; let patients choose a preferred contact method; track opt-in/engagement rates and follow up with low-engagement segments. |

Severity key:  High (6-9) — immediate attention    Medium (3-4) — monitor and manage    Low (1-2) — regular review

# Task 2: Contingency Plans for High-Priority Risks

For each High-severity risk, the contingency plan below outlines the reactive steps to take if the risk materializes despite mitigation, focused on minimizing disruption to patient care and recovering the project timeline.

| Risk ID | Risk Description | Contingency Plan |
| --- | --- | --- |
| OP-01 | Administrative schedulers resist adopting the automated conflict-prevention engine, continuing manual workarounds that reintroduce double-booking risk. | If resistance persists past the parallel-run period, mandate the automated engine as the system of record and disable manual overrides except through a logged exception process; assign trained super-users to shadow resistant staff for two additional weeks; escalate ongoing non-compliance to department leadership for a formal compliance directive. |
| OP-03 | Billing-issue resolution at discharge has no defined turnaround time, so the Admin/Billing bottleneck persists after automation. | If the SLA is breached repeatedly in a given week, stand up a temporary billing task force to clear the backlog within 48 hours; reassign cross-trained admin staff to billing during the surge; run a root-cause review of the exception types driving breaches and adjust the escalation rules accordingly. |
| OP-04 | Peak-hour congestion (Monday/weekend, 4-6 PM window) continues even after booking automation, since the root cause is staffing capacity, not scheduling conflicts alone. | If congestion continues despite rebalanced staffing, activate on-call float staff on short notice; open overflow appointment slots at adjacent facilities or extended hours; proactively notify affected patients of expected wait times via SMS/portal and offer rescheduling to lower-volume windows. |
| OP-05 | Severe workload imbalance (Orthopedics doctors averaging 7.86 usage hrs/day) is not resolved by scheduling automation alone, risking clinician burnout. | If dashboard alerts show sustained overload beyond the target threshold, trigger mandatory cross-department staff pooling within 24 hours; temporarily cap new Orthopedics bookings and redirect to General Medicine where clinically appropriate; engage HR and clinical leadership to arrange short-term locum or overtime coverage. |
| TE-02 | The scheduling/EHR platform experiences downtime or slow response during the 17:00-18:30 peak booking window, breaching the 99.9% uptime target. | If downtime occurs, failover to redundant infrastructure automatically and notify the IT on-call team immediately; activate the manual booking fallback at the front desk and call center so patient scheduling continues uninterrupted; conduct a post-incident root-cause review within 24 hours and log corrective actions. |
| TE-04 | The real-time conflict-detection engine fails to catch edge cases (concurrent bookings, sync lag), so double-bookings are reduced but not fully eliminated (AC-02 at risk). | If a double-booking occurs, resolve it immediately through the manual override queue and audit log; notify affected patients and offer priority rescheduling; log the specific edge case for the engineering team to address in the next patch cycle and track recurrence rate. |
| ST-05 | Patients continue to distrust or ignore automated SMS/Email notifications, so the 73.2% non-completion rate (no-shows, reschedules, cancellations) does not meaningfully improve. | If non-completion rates remain elevated after A/B testing, deploy live phone-call reminders for high-risk patient segments identified by the dashboard; partner with patient advocates or community liaisons for direct outreach; revisit notification content, timing, and channel strategy on a quarterly basis using engagement data. |

# Task 3: Risk Mitigation Plan Summary

## Mitigation Strategies

Mitigation strategies target the root causes surfaced across the Operational, Technical, and Stakeholder risk categories:

- Operational risks (OP-01 through OP-05) are addressed primarily through phased rollouts, structured change management, defined SLAs, and staffing/workload rebalancing informed by the live resource dashboard.

- Technical risks (TE-01 through TE-05) are addressed through security audits and encryption, load testing and redundant failover infrastructure, phased data migration with reconciliation checks, and preventive hardware maintenance.

- Stakeholder risks (ST-01 through ST-05) are addressed through simplified UI/UX design, consistent cross-functional communication cadences, direct clinician involvement in schedule-design decisions, and patient-preference-driven notification strategies.

## Contingency Plans

Contingency plans for the seven High-severity risks ensure the initiative can recover quickly if mitigation is insufficient — for example, activating failover infrastructure and manual booking fallback if the platform experiences downtime (TE-02), or standing up a temporary billing task force if the discharge billing SLA is breached (OP-03). Full contingency details are documented in Task 2 above.

## Alignment with Project Goals

These strategies and plans remain anchored to the initiative's acceptance criteria (AC-01 through AC-04) and the wait-time, satisfaction, and system-reliability targets defined in the Business Requirements Document, ensuring the plan supports — rather than duplicates — the project's existing goals and stakeholder expectations.

# Summary & Next Steps

- Prioritize continuous monitoring of the seven High-severity risks (OP-01, OP-03, OP-04, OP-05, TE-02, TE-04, ST-05) through weekly project status reviews during rollout.

- Track Medium-severity risks (OP-02, TE-01, TE-03, ST-01, ST-02, ST-04) through routine review cycles, escalating any that trend toward High severity.

- Maintain lightweight monitoring of the two Low-severity risks (TE-05, ST-03) without dedicating major resources unless conditions change.

- Revisit this Risk Matrix and Mitigation Plan at each project milestone to confirm strategies remain aligned with AC-01 through AC-04 and to update severity scores as mitigation actions take effect.

Source documents: Capstone_Project_M05L01_Risk_Register_SWOT.docx; HealthFirst_Care_Risk_Register.xlsx