RISK MANAGEMENT PLAN

Risk Register, Risk Assessment Matrix & SWOT Analysis

HealthFirst Care Initiative: Patient Experience & Operational Efficiency Overhaul

| Document Title: | Capstone_Project_M05L01_Risk_Register_SWOT.docx |
| --- | --- |
| Project Name: | HealthFirst Care Initiative |
| Author / Analyst: | Pritam Kar |
| Date | September 1, 2026 |

# Executive Summary

This Risk Management Plan documents the systematic identification, assessment, and mitigation of risks facing the HealthFirst Care Initiative, building on the findings of the Business Requirements Document (BRD), Requirements Traceability Matrix (RTM), Stakeholder Analysis, and As-Is/To-Be Process Models. Fifteen risks were identified across three categories — Operational, Technical, and Stakeholder — and each was scored for likelihood and impact to produce a prioritized Risk Register and a 3x3 Risk Assessment Matrix. A SWOT analysis closes out the plan with a strategic view of the initiative's strengths, weaknesses, opportunities, and threats.

# Task 1 & 2: Risk Register and Risk Assessment

Risks were identified from patient workflow analysis, resource allocation data, and stakeholder feedback trends gathered in earlier capstone modules, then categorized as Operational (workflow disruptions, staff resistance), Technical (data breaches, system downtime, integration failures), or Stakeholder (poor adoption, misaligned expectations). Each risk was scored on a 3-point Likelihood x Impact scale (Low = 1, Medium = 2, High = 3); the resulting product determines severity — High (6-9, immediate attention), Medium (3-4, monitor and manage), or Low (1-2, regular review).

| Risk ID | Risk Description | Category | Likelihood | Impact | Score | Severity | Mitigation Strategy |
| --- | --- | --- | --- | --- | --- | --- | --- |
| OP-01 | Administrative schedulers resist adopting the automated conflict-prevention engine, continuing manual workarounds that reintroduce double-booking risk. | Operational | Medium | High | 6 | High | Phased rollout with a parallel-run period; structured change-management plan with weekly hands-on training sessions for schedulers. |
| OP-02 | Mandatory staff training on kiosks and the new scheduling platform is incomplete before go-live, causing usage errors at launch. | Operational | Medium | Medium | 4 | Medium | Require training certification checkpoints prior to rollout; staff a dedicated super-user support desk for the first two weeks post-launch. |
| OP-03 | Billing-issue resolution at discharge has no defined turnaround time, so the Admin/Billing bottleneck persists after automation. | Operational | High | Medium | 6 | High | Define a service-level target (e.g., 2-hour resolution) for billing exceptions with automatic escalation to a billing supervisor when breached. |
| OP-04 | Peak-hour congestion (Monday/weekend, 4-6 PM window) continues even after booking automation, since the root cause is staffing capacity, not scheduling conflicts alone. | Operational | High | High | 9 | High | Rebalance staffing schedules toward Monday, weekend, and 4-6 PM shifts using the appointment volume trends already identified; add temporary float staff during peak windows. |
| OP-05 | Severe workload imbalance (Orthopedics doctors averaging 7.86 usage hrs/day) is not resolved by scheduling automation alone, risking clinician burnout. | Operational | Medium | High | 6 | High | Configure the live resource dashboard to trigger automatic workload-rebalancing alerts to leadership; establish a cross-department staff-pooling protocol for peak periods. |
| TE-01 | Cloud-enabled EHR integration with legacy patient-data architecture introduces a data breach or HIPAA compliance gap. | Technical | Low | High | 3 | Medium | Enforce role-based access control and end-to-end encryption (NFR-02); commission a third-party security audit and penetration test before go-live. |
| TE-02 | The scheduling/EHR platform experiences downtime or slow response during the 17:00-18:30 peak booking window, breaching the 99.9% uptime target. | Technical | Medium | High | 6 | High | Load-test the platform at 2x observed peak volume before launch; deploy redundant failover infrastructure with real-time uptime monitoring and alerting. |
| TE-03 | Interoperability issues between the new platform and the legacy database cause data integrity errors during integration. | Technical | Medium | Medium | 4 | Medium | Run a phased data migration with reconciliation checks against the legacy source; validate in a sandbox environment before production cutover. |
| TE-04 | The real-time conflict-detection engine fails to catch edge cases (concurrent bookings, sync lag), so double-bookings are reduced but not fully eliminated (AC-02 at risk). | Technical | Medium | High | 6 | High | Stress-test the conflict engine under concurrent-load scenarios; maintain a manual override queue with an audit log for administrative review. |
| TE-05 | Self-service kiosks or QR check-in hardware malfunction, forcing a fallback to manual paperwork and reintroducing the front-desk wait-time bottleneck. | Technical | Low | Medium | 2 | Low | Establish a preventive hardware maintenance schedule; keep a staffed manual backup lane available during outages. |
| ST-01 | Patients, particularly older or less tech-familiar users, show poor adoption of the web/mobile self-service portal, undermining the wait-time and satisfaction targets (AC-01, AC-03). | Stakeholder | Medium | Medium | 4 | Medium | Apply the simplified, multi-generational UI/UX design called for in NFR-03; provide on-site staff assistance for portal onboarding during the transition period. |
| ST-02 | Expectations diverge between IT & Operations (Keep Satisfied) and clinical Key Players on rollout timeline and feature priorities. | Stakeholder | Medium | Medium | 4 | Medium | Maintain the bi-weekly IT architecture syncs and weekly clinical status meetings defined in the Stakeholder Engagement Plan to keep priorities aligned. |
| ST-03 | Low engagement from Support & Maintenance staff (Monitor quadrant) leads to facility or equipment readiness gaps ahead of rollout milestones. | Stakeholder | Low | Medium | 2 | Low | Use intranet bulletins and scheduled facility-readiness check-ins tied to each project milestone date. |
| ST-04 | Doctors and nurses resist workload-rebalancing recommendations surfaced by the live resource dashboard (e.g., shifting load away from Orthopedics). | Stakeholder | Medium | Medium | 4 | Medium | Involve physicians and nurses directly in schedule-design feedback workshops; phase in rebalancing gradually and share transparent utilization data. |
| ST-05 | Patients continue to distrust or ignore automated SMS/Email notifications, so the 73.2% non-completion rate (no-shows, reschedules, cancellations) does not meaningfully improve. | Stakeholder | Medium | High | 6 | High | A/B test notification timing and channel; let patients choose a preferred contact method; track opt-in/engagement rates and follow up with low-engagement segments. |

## Risk Assessment Matrix

The matrix below visualizes each risk's Likelihood-vs-Impact placement, color-coded per the standard convention: Red = High severity (immediate attention), Yellow = Medium severity (monitor and manage), Green = Low severity (regular review).

| Likelihood ↓ / Impact → | Low | Medium | High |
| --- | --- | --- | --- |
| High | — | OP-03 | OP-04 |
| Medium | — | OP-02, TE-03, ST-01, ST-02, ST-04 | OP-01, OP-05, TE-02, TE-04, ST-05 |
| Low | — | TE-05, ST-03 | TE-01 |

# Task 3: SWOT Analysis

The SWOT analysis below evaluates the HealthFirst Care Initiative's internal strengths and weaknesses alongside external opportunities and threats, drawing on the same operational, technical, and stakeholder findings that informed the Risk Register.

| Strengths - Strong, engaged executive/leadership sponsorship (Key Players quadrant) backing the initiative. - Reliable, empirically validated baseline data — 216 appointment, 217 feedback, and 213 resource records analyzed. - Clear, quantified acceptance criteria (AC-01 through AC-04) that make success objectively measurable. - Formal BRD, RTM, and Stakeholder Engagement Plan already approved, giving the project a documented foundation. | Weaknesses - Core workflows (billing exception handling, room/equipment requests) remain manual with no defined turnaround SLAs. - Departmental data silos and legacy database interoperability constraints slow integration. - Significant resource/workload imbalance (Orthopedics 7.86 hrs/day) that scheduling automation alone will not fix. - Budget is capped to approved cap-ex allocations, limiting scope for additional remediation. |
| --- | --- |
| Opportunities - Automated conflict-detection engine and self-service kiosks can eliminate double-bookings and cut check-in time. - Staff training programs can accelerate adoption and reduce manual-process errors. - Live resource dashboard enables rebalancing idle capacity (General Medicine, Orthopedics) toward overburdened Pediatrics. - Phase 2 billing/financial system overhaul could close the remaining data-silo gap identified by IT & Operations. | Threats - Data breach or HIPAA non-compliance during legacy-to-cloud EHR integration. - Stakeholder resistance to change from administrative and clinical staff accustomed to manual workflows. - Patient distrust or low adoption of the automated notification system and self-service portal. - Continued peak-hour (4-6 PM, Monday/weekend) congestion if staffing is not rebalanced alongside the technology rollout. |

# Summary & Next Steps

- Prioritize the seven High-severity risks (OP-01, OP-03, OP-04, OP-05, TE-02, TE-04, ST-05) for immediate mitigation planning, since they concentrate around staffing/workload rebalancing, peak-hour capacity, and system reliability — the same themes surfaced throughout the BRD, process models, and swimlane analysis.

- Track Medium-severity risks (six identified) through routine project status reviews, revisiting their likelihood/impact scores as mitigation actions take effect.

- Maintain lightweight monitoring of the two Low-severity risks (TE-05, ST-03) without dedicating major resources unless conditions change.

- Revisit this Risk Register and SWOT analysis at each project milestone to confirm mitigation strategies remain aligned with the AC-01 through AC-04 acceptance criteria.

A companion Excel workbook (HealthFirst_Care_Risk_Register.xlsx) accompanies this document, containing the fully formula-driven Risk Register and an editable Risk Assessment Matrix.