## Risk_Register
HealthFirst Care Initiative — Risk Register | [7 empty] | Scale
Patient Experience & Operational Efficiency Overhaul ¦ Prepared by: Pritam Kar | [7 empty] | Low | 1
[8 empty] | Medium | 2
Risk ID | Risk Description | Risk Category | Likelihood | Impact | Severity Score | Severity Level | Mitigation Strategy | High | 3
OP-01 | Administrative schedulers resist adopting the automated conflict-prevention engine, continuing manual workarounds that reintroduce double-booking risk. | Operational | Medium | High | 6 | High | Phased rollout with a parallel-run period; structured change-management plan with weekly hands-on training sessions for Maria Carter/Jessica Gomes-level schedulers.
OP-02 | Mandatory staff training on kiosks and the new scheduling platform is incomplete before go-live, causing usage errors at launch. | Operational | Medium | Medium | 4 | Medium | Require training certification checkpoints prior to rollout; staff a dedicated super-user support desk for the first two weeks post-launch.
OP-03 | Billing-issue resolution at discharge has no defined turnaround time, so the Admin/Billing bottleneck identified in the swimlane analysis persists after automation. | Operational | High | Medium | 6 | High | Define a service-level target (e.g., 2-hour resolution) for billing exceptions with automatic escalation to a billing supervisor when breached.
OP-04 | Peak-hour congestion (Monday/weekend, 4-6 PM window) continues even after booking automation, since the root cause is staffing capacity, not scheduling conflicts alone. | Operational | High | High | 9 | High | Rebalance staffing schedules toward Monday, weekend, and 4-6 PM shifts using the appointment volume trends already identified; add temporary float staff during peak windows.
OP-05 | Severe workload imbalance (Orthopedics doctors averaging 7.86 usage hrs/day) is not resolved by scheduling automation alone, risking clinician burnout and care-quality issues. | Operational | Medium | High | 6 | High | Configure the live resource dashboard to trigger automatic workload-rebalancing alerts to leadership; establish a cross-department staff-pooling protocol for peak periods.
TE-01 | Cloud-enabled EHR integration with legacy patient-data architecture introduces a data breach or HIPAA compliance gap. | Technical | Low | High | 3 | Medium | Enforce role-based access control and end-to-end encryption (NFR-02); commission a third-party security audit and penetration test before go-live.
TE-02 | The scheduling/EHR platform experiences downtime or slow response during the 17:00-18:30 peak booking window, breaching the 99.9% uptime target. | Technical | Medium | High | 6 | High | Load-test the platform at 2x observed peak volume before launch; deploy redundant failover infrastructure with real-time uptime monitoring and alerting.
TE-03 | Interoperability issues between the new platform and the legacy database cause data integrity errors (duplicate or missing patient/appointment records) during integration. | Technical | Medium | Medium | 4 | Medium | Run a phased data migration with reconciliation checks against the legacy source; validate in a sandbox environment before production cutover.
TE-04 | The real-time conflict-detection engine fails to catch edge cases (e.g., concurrent bookings, sync lag), so double-bookings are reduced but not fully eliminated (AC-02 at risk). | Technical | Medium | High | 6 | High | Stress-test the conflict engine under concurrent-load scenarios; maintain a manual override queue with an audit log for administrative review.
TE-05 | Self-service kiosks or QR check-in hardware malfunction, forcing a fallback to manual paperwork and reintroducing the front-desk wait-time bottleneck. | Technical | Low | Medium | 2 | Low | Establish a preventive hardware maintenance schedule; keep a staffed manual backup lane available during outages.
ST-01 | Patients, particularly older or less tech-familiar users, show poor adoption of the web/mobile self-service portal, undermining the wait-time and satisfaction targets (AC-01, AC-03). | Stakeholder | Medium | Medium | 4 | Medium | Apply the simplified, multi-generational UI/UX design called for in NFR-03; provide on-site staff assistance for portal onboarding during the transition period.
ST-02 | Expectations diverge between IT & Operations (Keep Satisfied quadrant) and clinical Key Players on rollout timeline and feature priorities. | Stakeholder | Medium | Medium | 4 | Medium | Maintain the bi-weekly IT architecture syncs and weekly clinical status meetings defined in the Stakeholder Engagement Plan to keep priorities aligned.
ST-03 | Low engagement from Support & Maintenance staff (Monitor quadrant) leads to facility or equipment readiness gaps ahead of rollout milestones. | Stakeholder | Low | Medium | 2 | Low | Use intranet bulletins and scheduled facility-readiness check-ins tied to each project milestone date.
ST-04 | Doctors and nurses resist workload-rebalancing recommendations surfaced by the live resource dashboard (e.g., shifting load away from Orthopedics). | Stakeholder | Medium | Medium | 4 | Medium | Involve physicians and nurses directly in schedule-design feedback workshops; phase in rebalancing gradually and share transparent utilization data.
ST-05 | Patients continue to distrust or ignore automated SMS/Email notifications, so the 73.2% non-completion rate (no-shows, reschedules, cancellations) does not meaningfully improve. | Stakeholder | Medium | High | 6 | High | A/B test notification timing and channel; let patients choose a preferred contact method; track opt-in/engagement rates and follow up with low-engagement segments.
Severity Legend:
High (score 6-9) — Immediate attention
Medium (score 3-4) — Monitor and manage
Low (score 1-2) — Regular review

## Risk_Assessment_Matrix
HealthFirst Care Initiative — Risk Assessment Matrix (3x3)
Likelihood (rows) vs. Impact (columns) — cell shows Risk IDs falling into that combination
| Impact → | Low | Medium | High
Likelihood ↓ | High | — | OP-03 | OP-04
| Medium | — | OP-02 TE-03 ST-01 ST-02 ST-04 | OP-01 OP-05 TE-02 TE-04 ST-05
| Low | — | TE-05 ST-03 | TE-01
High severity (score 6-9) — Immediate attention
Medium severity (score 3-4) — Monitor and manage
Low severity (score 1-2) — Regular review